## Data
Data Quality Issues Log 2024
ID | Issue Title | Severity | Status | System | Table | Column | Error Count | Impact | Opened Date | Owner | Root Cause | Target Date | Resolution Note
DQI-001 | Missing National IDs | **CRITICAL** | Open | EHR | PATIENT | NAT_ID | 450 | Legal Compliance | 2024-10-01 | Medical Dir | Emergency Admission | 2025-01-30 | Call campaign started.
DQI-002 | Invalid Email Formats | HIGH | In Progress | CRM | CUSTOMER | EMAIL | 12,500 | Marketing fail | 2024-10-05 | Sales Dir | No Input Validation | 2025-02-15 | API Check being built.
DQI-003 | Duplicate Vendors | HIGH | Open | ERP | VENDOR | NAME | 45 | Payment Errors | 2024-10-10 | Finance Dir | Manual Entry | 2025-01-20 | Merging records.
DQI-004 | Null DOBs | MEDIUM | Resolved | HR | EMPLOYEES | DOB | 12 | Pension Calc | 2024-10-12 | HR Dir | Migration Bug | 2024-10-20 | Added NOT NULL constraint.
DQI-005 | Future Dates | HIGH | Resolved | EHR | VISIT | VISIT_DATE | 5 | Reports skew | 2024-10-15 | IT Ops | System Clock Drift | 2024-10-16 | NTP Server fixed.
DQI-006 | Negative Salaries | **CRITICAL** | Resolved | Payroll | PAYROLL | AMOUNT | 2 | Financial Loss | 2024-10-18 | Finance Dir | Typo | 2024-10-19 | Money recovered.
DQI-007 | Invalid Country Codes | LOW | Open | CRM | ADDRESS | CNTRY | 1,500 | Mail delivery | 2024-10-20 | Sales Dir | Free text field | 2025-03-01 | Converting to Dropdown.
DQI-008 | Missing Gender | MEDIUM | In Progress | EHR | PATIENT | GENDER | 300 | Clinical Stats | 2024-10-25 | Medical Dir | Optional field | 2025-01-30 | Updating UI.
DQI-009 | Product Price Zero | HIGH | Resolved | SCM | PRODUCT | PRICE | 10 | Revenue Loss | 2024-11-01 | Sales Dir | Loading Error | 2024-11-02 | Reloaded price list.
DQI-010 | Orphaned Orders | MEDIUM | Open | ERP | ORDERS | CUST_ID | 25 | Reporting | 2024-11-05 | IT Ops | Delete logic flaw | 2025-02-01 | Fixing code.
DQI-011 | Special Chars in Name | LOW | Open | HR | EMPLOYEES | NAME | 55 | Badge Printing | 2024-11-08 | HR Dir | Copypaste from web | 2025-03-01 | Cleaning script.
DQI-012 | Wrong Date Format | LOW | Resolved | CRM | ACTIVITY | DATE | 500 | Dashboard | 2024-11-10 | IT Ops | US vs UK format | 2024-11-12 | Standardized to ISO.
DQI-013 | IBAN Length Error | **CRITICAL** | Resolved | ERP | VENDOR | IBAN | 3 | Pmt Rejection | 2024-11-15 | Finance Dir | Typo | 2024-11-15 | Corrected manually.
DQI-014 | Expired Passports | HIGH | In Progress | HR | EMPLOYEES | PPT_EXP | 45 | Visa Issues | 2024-11-20 | HR Dir | Emp negligence | 2025-01-15 | Identifying alerts.
DQI-015 | Empty Asset Locations | MEDIUM | Open | Maximo | ASSET | LOC_ID | 200 | Loss of Asset | 2024-11-25 | Ops Dir | Mobile App Sync | 2025-02-20 | Fixing sync.
DQI-016 | Duplicate Tweets | LOW | Open | Social | POSTS | ID | 500 | Analytics | 2024-11-28 | Marketing | API Retry logic | 2025-03-01 | Deduplicating in DW.
DQI-017 | Missing Zip Codes | LOW | In Progress | CRM | ADDRESS | ZIP | 4,000 | Geo-marketing | 2024-12-01 | Sales Dir | Old Data | 2025-06-01 | Buying external data.
DQI-018 | Inactive Users Active | **CRITICAL** | Resolved | AD | USER | STATUS | 10 | Security Risk | 2024-12-02 | CISO | Leaver Process | 2024-12-02 | Accounts disabled.
DQI-019 | Missing Blood Type | HIGH | Open | EHR | PATIENT | BLOOD | 120 | Surgery Risk | 2024-12-05 | Medical Dir | Data migration | 2025-01-30 | Retesting patients.
DQI-020 | Negative Inventory | HIGH | Open | SCM | STOCK | QTY | 15 | Ordering error | 2024-12-08 | Ops Dir | Sync delay | 2025-02-01 | Real-time sync.
DQI-021 | Test Data in Prod | MEDIUM | Resolved | CRM | CUSTOMER | NAME | 5 | Confusion | 2024-12-10 | IT Ops | Dev testing | 2024-12-10 | Deleted 'John Doe'.
DQI-022 | Missing Supplier Tax ID | **CRITICAL** | Open | ERP | VENDOR | VAT_ID | 20 | ZATCA Fine | 2024-12-12 | Finance Dir | New Regs | 2025-01-15 | Contacting vendors.
DQI-023 | Currency Mismatch | HIGH | Resolved | ERP | INVOICE | CURR | 8 | GL Error | 2024-12-15 | Finance Dir | Default USD | 2024-12-16 | Corrected to SAR.
DQI-024 | URL Broken | LOW | Open | CMS | CONTENT | URL | 50 | Bad UX | 2024-12-18 | Comms Dir | Page move | 2024-12-30 | Redirects set.
DQI-025 | Missing Manager ID | MEDIUM | Open | HR | EMPLOYEES | MGR_ID | 15 | Workflow stuck | 2024-12-20 | HR Dir | Org restructure | 2025-01-10 | Assigning mgrs.
DQI-026 | Overlapping Shifts | MEDIUM | Open | HR | SHIFT | TIME | 40 | Pay calc | 2024-12-21 | HR Ops | Input error | 2025-02-01 | Validation rule.
DQI-027 | Patient Age > 120 | LOW | Resolved | EHR | PATIENT | DOB | 2 | Data entry | 2024-12-22 | Medical Dir | Typo 1890 | 2024-12-22 | Fixed to 1990.
DQI-028 | PO Amount < 0 | HIGH | Resolved | Procurement | PO | AMT | 1 | Fraud risk | 2024-12-23 | Audit | Glitch | 2024-12-23 | Cancelled PO.
DQI-029 | Missing Ethnicity | LOW | Open | HR | EMPLOYEES | ETHNIC | 200 | Diversity Rpt | 2024-12-24 | HR Dir | Optional | 2025-06-01 | Survey run.
DQI-030 | Vehicle Reg Expired | HIGH | Open | Fleet | VEHICLE | REG_EXP | 12 | Fines | 2024-12-25 | Ops Dir | Oversight | 2025-01-05 | Renewing.
DQI-031 | Duplicate SKU | HIGH | Open | SCM | PRODUCT | SKU | 5 | Ordering | 2024-12-26 | Ops Dir | Vendor merge | 2025-01-30 | Remapping SKUs.
DQI-032 | Missing Cost Center | MEDIUM | Open | ERP | EXPENSE | CC_ID | 50 | Budgeting | 2024-12-27 | Finance Dir | User skipped | 2025-02-01 | Mandatory field.
DQI-033 | Invalid Phone Length | LOW | Open | CRM | CONTACT | PHONE | 300 | SMS fail | 2024-12-28 | Sales Dir | Old data | 2025-03-01 | Cleaning.
DQI-034 | Generic Name 'Unknown' | MEDIUM | Open | CRM | CUSTOMER | NAME | 100 | Bad CX | 2024-12-29 | Sales Dir | Migration default | 2025-04-01 | Investigation.
DQI-035 | Missing Doctor ID | **CRITICAL** | Resolved | EHR | PRESCRIPT | DOC_ID | 10 | Legal | 2024-12-30 | Medical Dir | System Error | 2024-12-30 | Database patched.
DQI-036 | Lab Result No Units | **CRITICAL** | Open | LIMS | RESULT | UNIT | 5 | Safety | 2024-12-30 | Medical Dir | Interface bug | 2025-01-05 | Code fix.
DQI-037 | Missing Admission Dt | HIGH | Open | EHR | VISIT | ADM_DT | 20 | Billing | 2024-12-30 | Medical Dir | Paper process | 2025-01-15 | Manual entry.
DQI-038 | Duplicate Assets | MEDIUM | Open | Maximo | ASSET | SERIAL | 15 | Inventory | 2024-12-30 | Ops Dir | Scanning error | 2025-02-01 | Phyiscal audit.
DQI-039 | Missing Building ID | LOW | Open | Fleet | TRIP | BLDG_ID | 500 | Analysis | 2024-12-30 | Ops Dir | GPS drift | 2025-03-01 | Geofencing fix.
DQI-040 | Missing Project End Dt | MEDIUM | Open | Jira | TASK | END_DT | 50 | Planning | 2024-12-30 | PMO | User error | 2025-02-01 | Training.
DQI-041 | Budget > Limit | HIGH | Resolved | Hyperion | BUDGET | AMT | 1 | Finance Ctrl | 2024-12-30 | CFO | Excel upload | 2024-12-30 | Rejected upload.
DQI-042 | Missing Contract PDF | **CRITICAL** | Open | Ariba | CONTRACT | ATT | 5 | Audit Fail | 2024-12-30 | Legal | Scan fail | 2025-01-10 | Rescanning.
DQI-043 | Invalid Region | LOW | Open | CRM | ADDRESS | REGION | 200 | Territory | 2024-12-30 | Sales Dir | Typo | 2025-03-01 | Bulk update.
DQI-044 | Missing Marital Stat | LOW | Open | HR | EMPLOYEES | MARITAL | 50 | Insurance | 2024-12-30 | HR Dir | New hires | 2025-01-30 | Asking employees.
DQI-045 | Terminated User login | **CRITICAL** | Resolved | AD | LOGS | USER_ID | 1 | Security | 2024-12-30 | CISO | Timing issue | 2024-12-30 | Access revoked.
DQI-046 | Missing Invoice Date | HIGH | Open | ERP | INVOICE | DATE | 10 | Payment | 2024-12-30 | Finance Dir | OCR fail | 2025-01-10 | Manual check.
DQI-047 | Mixed Case Names | LOW | Open | CRM | CUSTOMER | NAME | 5,000 | Aesthetics | 2024-12-30 | Sales Dir | User entry | 2025-04-01 | Standardization.
DQI-048 | Missing Emergency Ct | HIGH | Open | HR | EMPLOYEES | EM_CONT | 100 | Safety | 2024-12-30 | HR Dir | New policy | 2025-02-01 | Campaign.
DQI-049 | Lead Source Unknown | LOW | Open | CRM | LEAD | SOURCE | 1,000 | Mktg ROI | 2024-12-30 | Marketing | Web form | 2025-03-01 | Fixing dropdown.
DQI-050 | Missing Lat/Long | MEDIUM | Open | Fleet | STOP | COORD | 200 | Routing | 2024-12-30 | Ops Dir | Device offline | 2025-02-01 | Device replace.
DQI-051 | Duplicate Invoice ID | **CRITICAL** | Resolved | ERP | INVOICE | ID | 2 | Double Pay | 2024-12-30 | Finance | Vendor error | 2024-12-30 | Rejected 2nd.
DQI-052 | Missing Job Title | MEDIUM | Open | HR | EMPLOYEES | TITLE | 10 | Org Chart | 2024-12-30 | HR Dir | SAP Sync | 2025-01-15 | Manual fix.
DQI-053 | Price Variance > 20% | HIGH | Open | Procurement | PO | PRICE | 5 | Cost control | 2024-12-30 | Finance | Inflation? | 2025-01-10 | Reviewing.
DQI-054 | Zero Quantity Order | LOW | Resolved | CRM | ORDER | QTY | 20 | Null order | 2024-12-30 | IT Ops | App bug | 2024-12-30 | Deleted.
DQI-055 | Missing Training Hrs | LOW | Open | LMS | COURSE | HRS | 50 | Reporting | 2024-12-30 | HR Dir | Meta missing | 2025-02-01 | Updating courses.
DQI-056 | Invalid Postcode | LOW | Open | CRM | ADDRESS | POST | 150 | Shipping | 2024-12-30 | Sales Dir | User error | 2025-03-01 | Validation.
DQI-057 | Missing Serial # | HIGH | Open | Maximo | ASSET | SERIAL | 30 | Warranty | 2024-12-30 | Ops Dir | Label missing | 2025-01-30 | Physical check.
DQI-058 | Survey Score > 10 | MEDIUM | Resolved | Survey | RESULT | SCORE | 5 | Scale 1-10 | 2024-12-30 | Marketing | Bug | 2024-12-30 | Normalized.
DQI-059 | Null Ticket Category | MEDIUM | Open | ServiceNow | TICKET | CAT | 100 | Routing | 2024-12-30 | IT Ops | Email ingest | 2025-02-01 | AI Classifier.
DQI-060 | Old Open Tickets | LOW | Open | ServiceNow | TICKET | AGE | 500 | SLA Stats | 2024-12-30 | IT Ops | Neglect | 2025-02-01 | Bulk close.
DQI-061 | Missing Vendor Email | HIGH | Open | ERP | VENDOR | EMAIL | 20 | PO Delivery | 2024-12-30 | Procurement | Phone only | 2025-01-20 | Calling.
DQI-062 | Invalid Tax Rate | **CRITICAL** | Resolved | ERP | INVOICE | TAX | 3 | Compliance | 2024-12-30 | Finance | Old rate | 2024-12-30 | Corrected.
DQI-063 | Missing Bank Name | HIGH | Open | HR | PAYROLL | BANK | 5 | Salary fail | 2024-12-30 | HR Dir | New hire | 2025-01-20 | Asking emp.
DQI-064 | Duplicate Badges | **CRITICAL** | Resolved | Lenel | BADGE | ID | 1 | Security | 2024-12-30 | Security | Printing err | 2024-12-30 | Voided one.
DQI-065 | Missing Visitor Host | MEDIUM | Open | Visitor | VISIT | HOST | 20 | Security | 2024-12-30 | Security | Reception bypass | 2025-01-10 | Training.
DQI-066 | Asset Life < 0 | LOW | Open | Maximo | ASSET | AGE | 5 | Planning | 2024-12-30 | Ops Dir | Calc error | 2025-02-01 | Formula fix.
DQI-067 | Missing Menu Price | LOW | Open | POS | ITEM | PRICE | 2 | Revenue | 2024-12-30 | Admin | New item | 2024-12-30 | Added.
DQI-068 | Missing Room Cap | LOW | Open | Outlook | ROOM | CAP | 10 | Booking | 2024-12-30 | Admin | Setup | 2025-01-15 | Measuring.
DQI-069 | Negative Leave Bal | HIGH | Open | HR | LEAVE | BAL | 15 | Payroll | 2024-12-30 | HR Dir | Overuse | 2025-01-20 | Adjustment.
DQI-070 | Missing Flight No | MEDIUM | Open | Travel | TRIP | FLIGHT | 10 | Tracking | 2024-12-30 | Admin | Booking err | 2025-01-10 | Updating.
DQI-071 | Missing Driver Lic | **CRITICAL** | Open | Fleet | DRIVER | LIC | 5 | Legal | 2024-12-30 | Ops Dir | Expired | 2025-01-05 | Suspension.
DQI-072 | Invalid GL Account | HIGH | Resolved | ERP | JOURNAL | GL | 10 | Closing | 2024-12-30 | Finance | Typo | 2024-12-30 | Reclassed.
DQI-073 | Missing Project Mgr | HIGH | Open | Jira | PROJ | MGR | 5 | Accountability | 2024-12-30 | PMO | Leaver | 2025-01-15 | Reassigning.
DQI-074 | Task Desc 'Test' | LOW | Resolved | Jira | TASK | DESC | 20 | Junk data | 2024-12-30 | PMO | Testing | 2024-12-30 | Deleted.
DQI-075 | Missing Resolution | MEDIUM | Open | ServiceNow | TICKET | RES | 50 | Knowledge | 2024-12-30 | IT Ops | Lazy closing | 2025-02-01 | Mandatory field.
DQI-076 | Server IP Conflict | **CRITICAL** | Resolved | CMDB | CI | IP | 2 | Outage Risk | 2024-12-30 | Network | Manual assign | 2024-12-30 | DHCP fixed.
DQI-077 | Missing OS Version | MEDIUM | Open | CMDB | CI | OS | 100 | Patching | 2024-12-30 | Security | Discovery fail | 2025-02-01 | Agent reinstall.
DQI-078 | Unknown App Owner | HIGH | Open | CMDB | APP | OWNER | 10 | Support | 2024-12-30 | IT Arch | Legacy | 2025-03-01 | Identifying.
DQI-079 | Missing Lic Exp Date | HIGH | Open | Snow | LIC | EXP | 20 | Compliance | 2024-12-30 | IT Proc | Data entry | 2025-01-30 | Updating.
DQI-080 | Duplicate Hostname | MEDIUM | Resolved | CMDB | CI | NAME | 5 | Confusion | 2024-12-30 | IT Ops | Decom fail | 2024-12-30 | Removed old.
DQI-081 | Missing Backup Log | **CRITICAL** | Open | Veeam | JOB | LOG | 2 | Recovery Risk | 2024-12-30 | IT Ops | Agent crash | 2025-01-02 | Restart.
DQI-082 | Missing Room Temp | HIGH | Open | BMS | ROOM | TEMP | 5 | Server Heat | 2024-12-30 | Ops Dir | Sensor dead | 2025-01-10 | Replace sensor.
DQI-083 | Unknown MAC Addr | MEDIUM | Open | Network | DEVICE | MAC | 50 | Security | 2024-12-30 | Network | BYUOD | 2025-02-01 | NAC Config.
DQI-084 | Invalid User Name | LOW | Open | AD | USER | NAME | 2 | Aesthetics | 2024-12-30 | IT Ops | Typo | 2025-01-15 | Correcting.
DQI-085 | Missing Dept Code | MEDIUM | Open | HR | EMPLOYEES | DEPT | 5 | Cost Alloc | 2024-12-30 | HR Dir | Org Change | 2025-01-20 | Updating.
DQI-086 | Invalid Shift Code | LOW | Open | HR | SHIFT | CODE | 10 | Planning | 2024-12-30 | HR Ops | Old codes | 2025-02-01 | Removing.
DQI-087 | Missing Skill Tag | LOW | Open | HR | EMPLOYEES | SKILL | 400 | Talent Mgmt | 2024-12-30 | HR Dir | New feature | 2025-06-01 | Survey.
DQI-088 | Duplicate PO | HIGH | Resolved | Procurement | PO | NUM | 1 | Error | 2024-12-30 | Finance | System glitch | 2024-12-30 | Cancelled.
DQI-089 | Missing Rectpt Date | HIGH | Open | Procurement | GRN | DATE | 5 | Payment | 2024-12-30 | Warehouse | Delay | 2025-01-10 | Entry.
DQI-090 | Asset Value 0 | HIGH | Open | Finance | ASSET | VAL | 10 | Balance Sheet | 2024-12-30 | Finance | Migration | 2025-02-01 | Valuation.
DQI-091 | Depreciation Error | HIGH | Open | Finance | ASSET | DEP | 5 | Audit | 2024-12-30 | Finance | Formula | 2025-02-01 | Recalc.
DQI-092 | Missing Patient Addr | HIGH | Open | EHR | PATIENT | ADDR | 50 | Billing | 2024-12-30 | Medical | Emergency | 2025-01-30 | Calling.
DQI-093 | Invalid diagnosis | HIGH | Open | EHR | VISIT | DIAG | 10 | Coding | 2024-12-30 | Medical | Typo | 2025-01-15 | correcting.
DQI-094 | Missing Prescrip Dt | **CRITICAL** | Open | Pharmacy | RX | DATE | 5 | Safety | 2024-12-30 | Medical | Error | 2025-01-05 | Investigation.
DQI-095 | Wrong Drug Units | **CRITICAL** | Open | Pharmacy | RX | UNIT | 2 | Safety | 2024-12-30 | Medical | Typo | 2025-01-05 | Fixing mg/ml.
DQI-096 | Duplicate Lab Order | MEDIUM | Resolved | LIMS | ORDER | ID | 10 | Waste | 2024-12-30 | Lab | User double click | 2024-12-30 | Cancelled.
DQI-097 | Missing Sample Temps | HIGH | Open | LIMS | SAMPLE | TEMP | 15 | Quality | 2024-12-30 | Lab | Logger fail | 2025-01-10 | Maintenance.
DQI-098 | Missing Report Desc | LOW | Open | PowerBI | RPT | DESC | 50 | Catlaog | 2024-12-30 | Analytics | Lazy Devs | 2025-03-01 | Update meta.
DQI-099 | Unused Reports | LOW | Open | PowerBI | RPT | USAGE | 20 | Clutter | 2024-12-30 | Analytics | Old | 2025-04-01 | Archive.
DQI-100 | Slow Query Log | MEDIUM | Open | Oracle | QUERY | TIME | 5 | Performance | 2024-12-30 | DBA | Bad Index | 2025-01-20 | Tuning.